## TestCase
Product Name |  | book-valley | TC Start Date | 31/8/2024 | TC Execution Start Date | - - |  |  |  |  | TEST CASE
Module Name |  | Home Page | TC End Date |  | TC Execution End Date | - - |  |  |  |  | PASS | 57
Epic |  |  | Test Case Developed By | Md. Abu Talha | Browser (tested) | Yes |  |  |  |  | FAIL | 18
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) | Yes |  |  |  |  | NO RUN | 43
Test Executed by | [10 empty] | BLOCKED | 0
[11 empty] | TOTAL | 118
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bugs Screen Shot | Dev Comments | Final Status | Remarks
1 |  | Browser Compatibility Testing | Account | Checking by running the URL site in different browsers. | Should be run in different browsers. | Found as per expectation. | Browsers-Chrome, Internet Explorer, Mozilla Firefox, Microsoft Edge, Opera Mini. | 1. Go to different browsers. 2. Search 'Startech' 3. Go to the website. |  |  | Passed
2 | Home Page |  | Header | Verify the header section is added to the website | should be present header section and visible. | Found as per expectation | Visiable check | 1. go to https://book-valley-72490.web.app/ 2. check the visiable |  |  | Passed
3 |  |  |  | Verify all links in the header are functional. | All links should open the corresponding pages | Found as per expectation | ALl Link click and check functional | 1. go to https://book-valley-72490.web.app/ 2. click and check all link is functional |  |  | Passed
4 |  |  |  | Verify the search bar is added to the header menu | The search bar should be present. | Did not found as per expectation | have to see search bar | 1. go to https://book-valley-72490.web.app/ 2. Inspect the header for a search bar | No search bar in header |  | Failed
5 |  |  |  | Verify the header section is aligned | All elements should be aligned properly. | found as per expectation | check the alignment | 1. go to https://book-valley-72490.web.app/ 2.Observe the alignment of header elements. |  |  | Passed
6 |  |  |  | Verify the header’s response to mouse hover on links | Link color should change on hover. | found as per expectation | CHeck the color chenge | Hover over each link in the header. |  |  | Passed
7 |  |  |  | Verify the home page opens on clicking the logo from any page. | The home page should load. | Did not found as per expectation | N/A | 1. go to https://book-valley-72490.web.app/ 2.Click the website logo in the header. | Did not response logo |  | Failed
8 |  |  |  | Verify the correct page opens upon clicking a header link | Each link should navigate to the correct page | found as per expectation | N/A | 1. go to https://book-valley-72490.web.app/ 2.Click each link in the header |  |  | Passed
9 |  |  |  | Verify that the selected header link remains active. | The clicked link should stay active. | found as per expectation | N/A | 1. go to https://book-valley-72490.web.app/ 2. Click on any header link. Observe if the link remains highlighted or marked as active. |  |  | Passed
10 |  |  |  | Verify the header is sticky or fixed as per the design requirements. | should either stick to the top or behave as designed. | found as per expectation | N/A | 1. go to https://book-valley-72490.web.app/ 2. Scroll up and down on the page. |  |  | Passed
11 |  |  |  | Verify that icons in the header are aligned with the text. | Icons should be aligned correctly with the text. | found as per expectation | N/A | 1. go to https://book-valley-72490.web.app/ 2.Observe the position of icons relative to their corresponding text. |  |  | Passed
12 |  |  |  | Verify that the icons added are related to the link text | Icons should be relevant to the link content. | found as per expectation | N/A | 1. go to https://book-valley-72490.web.app/ 2.Compare the icons with their corresponding link text. |  |  | Passed
13 |  |  |  | Verify the header is consistent across all pages | The header should be the same on every page. | found as per expectation | N/A | 1. go to https://book-valley-72490.web.app/ 2.Navigate through various pages of the website.. |  |  | Passed
14 |  |  |  | Verify that the header and body section are distinguishable. | The header should be clearly distinguishable from the body. | found as per expectation | N/A | 1. go to https://book-valley-72490.web.app/ 2.Observe the visual contrast between the header and body. |  |  | Passed
15
16
17 |  |  | Footer | Verify the footer section is aligned at the end of the page. | The footer is positioned at the very bottom of the page without overlapping or misalignment. | Found as per expextation |  | Scroll to the bottom of the page on different screen resolutions. |  |  | Passed
18 |  |  |  | Verify there is no extra white space at the end of the footer on high-screen resolutions | should be no unnecessary white space below the footer on high-resolution screens. | Found as per expextation |  | View the page on a high-resolution screen and observe the footer section |  |  | Passed
19 |  |  |  | Verify elements are aligned correctly in the footer section | All elements within the footer (text, links, icons, etc.) are properly aligned | Found as per expextation |  | Inspect the footer section layout on the webpage. |  |  | Passed
20 |  |  |  | Verify the footer section is consistent across all pages. | The footer section looks the same on all website pages. | Found as per expextation |  | Navigate through different pages and observe the footer |  |  | Passed
21 |  |  |  | Verify the logo is displayed in the footer | The company logo is present in the footer section | Found as per expextation |  | Inspect the footer for the logo |  |  | Passed
22 |  |  |  | Verify the logo is aligned correctly in the footer. | The logo is properly aligned (centered, left, or right as per design) in the footer section. | Found as per expextation |  | Inspect the alignment of the logo in the footer. |  |  | Passed
23 |  |  |  | Verify clicking on the logo redirects to the home page | Clicking the logo takes the user to the home page. | didnot found as per expectation |  | Click on the logo in the footer. | footer logo did not responded |  | Failed
24 |  |  |  | Verify clicking on footer links navigates to the correct pages | Each link in the footer navigates to its intended page | didnot found as per expectation |  | Click on each link in the footer and verify the destination page. | footer all link did not work |  | Failed
25 |  |  |  | Verify all social links with icons are present in the footer | All intended social media icons and links are displayed in the footer. | found as per expectation |  | Inspect the footer for the presence of social media icons |  |  | Passed
26 |  |  |  | Verify there are no spelling mistakes in the footer text. | All text in the footer is spelled correctly | found as per expectation |  | Review the footer text for spelling errors. |  |  | Passed
27 |  |  |  | Verify equal spacing for elements (links, buttons, social icons) in the footer. | All elements in the footer have equal spacing from the top and bottom. | found as per expectation |  | Inspect the spacing around elements in the footer. |  |  | Passed
28 |  |  |  | Verify there are no broken links in the footer. | All links in the footer are functional and do not lead to error pages. | found as per expectation |  | Click on all footer links to verify their functionality. | Link did not work same as previous bug |  | Failed
29 |  |  |  | Verify the presence of a newsletter subscription section in the footer. | The newsletter subscription section is present in the footer. | Didnot found as per expectation |  | Inspect the footer for the newsletter subscription section | No News letter in the header |  | Failed
30 |  |  |  | Verify the subscription email field and subscribe button are present. | The email input field and the subscribe button are present in the footer. | Didnot found as per expectation |  | Check the newsletter subscription section. | No subscription in the header |  | Failed
31 |  |  |  | Verify the presence of the copyright section in the footer. | The copyright text is displayed in the footer. | found as per expectation |  | Inspect the footer for the copyright section. |  |  | Passed
32 |  |  |  | Verify all social linkks perfectly open with the correct page | Should open the all social media link | Did'nt found as per expectation |  | 1. go to url 2. go to the footer 3. click the all link step by step | social media link doed not open |  | Failed
33
34
35 |  |  | Contact US | Verify the presence of the "Contact Us" section on the Homepage | Should display the "Contact Us" section on the Homepage. | Found as per expectation | N/A | 1. Navigate to the homepage of the website. 2.Scroll down to locate the "Contact Us" section. |  |  | Passed
36 |  |  |  | Verify the presence of the "Name" field in the "Contact Us" section | Should display the "Name" field where users can input their names. | Found as per expectation | N/A | 1. Navigate to the "Contact Us" section on the homepage. 2. Check for the presence of the "Name" field. |  |  | Passed
37 |  |  |  | Verify the presence of the "Email" field in the "Contact Us" section | Should display the "Email" field where users can input their email addresses. | Found as per expectation | N/A | 1. Navigate to the "Contact Us" section on the homepage. 2. Check for the presence of the "Email" field. |  |  | Passed
|  |  |  | Verify the presence of the "Message" field in the "Contact Us" section. | Should display the "Message" field where users can input their messages | Found as per expectation | N/A | 1. Navigate to the "Contact Us" section on the homepage. 2. Check for the presence of the "Message" field. |  |  | Passed
|  |  |  | Verify the text displayed in the "Contact Us" section | Should display the correct text as mentioned above | Found as per expectation | We are always waiting to receive your question and opinion. Please feel free to contact with us | 1. Navigate to the "Contact Us" section on the homepage. 2. Verify that the correct text is displayed as mentioned above. |  |  | Passed
|  |  |  | Verify the form submission without any input | Should display an error message for each mandatory field when the form is submitted with empty fields. | did not found as per expectation | Name: (Leave blank) Email: (Leave blank) Message: (Leave blank) | 1. Navigate to the "Contact Us" section on the homepage. 2. Leave all fields blank. Attempt to submit the form. | Did not show the error message |  | Failed
|  |  |  | Verify the validation of the "Email" field when an invalid email format is entered. | Should display an error message indicating that the email format is incorrect. | found as per expectation | Name: "John Doe" Email: "userexample.com" (invalid format) Message: "This is a test message." | 1. Navigate to the "Contact Us" section on the homepage. 2. Enter an invalid email format in the "Email" field. 3. Attempt to submit the form. |  |  | Passed
|  |  |  | Verify the form submission with valid data in all fields | Should successfully submit the form and display a confirmation message that the message has been sent. | Did not found as per expectation | Name: "John Doe" Email: "john.doe@example.com" Message: "This is a test message." | 1. Navigate to the "Contact Us" section on the homepage. 2. Enter valid data in the "Name," "Email," and "Message" fields. 3. Submit the form. | Did not send message |  | Failed
|  |  |  | Verify that the "Name" field rejects excessively long input. | Should display an error message indicating that the name is too long and must be shortened. | found as per expectation | Name: "Johnathan Michael Doe Smith Johnson Williams Brown Taylor Anderson Thompson" (overly long name) | 1. Navigate to the "Contact Us" section on the homepage. 2. Enter an excessively long name in the "Name" field. 3. Attempt to submit the form. |  |  | Passed
|  |  |  | Verify that the "Email" field rejects input without the "@" symbol | Should display an error message indicating that the email address is not valid | found as per expectation | Email: "johndoemail.com" (missing '@' symbol) | 1. Navigate to the "Contact Us" section on the homepage. 2. Enter an email address without the "@" symbol in the "Email" field. 3.Attempt to submit the form. |  |  | Passed
|  |  |  | Verify that the "Message" field rejects excessively long input | Should display an error message indicating that the message is too long and must be shortened. | did not found as per expectation | Message: (Enter a message with more than 1000 characters) | 1. Navigate to the "Contact Us" section on the homepage. 2. Enter an overly long 3. message in the "Message" field. Attempt to submit the form. | Not Respone to the server | Did not respone with the server | Failed
|  |  |  | Verify that the form submission process is secure. | Should securely submit the form data using HTTPS without exposing any sensitive information. | did not found as per expectation | Name: "John Doe" Email: "john.doe@example.com" Message: "This is a test message." | 1. Navigate to the "Contact Us" section on 2. the homepage. Enter valid data in all fields. 3. Monitor the network requests to ensure data is being sent securely (e.g., via HTTPS). | Not Respone to the server |  | Failed
|  |  |  | Verify that an appropriate error message is shown when the email field is left blank. | Should display an error message indicating that the email field is required. | did not found as per expectation | Name: "John Doe" Email: (Leave blank) Message: "This is a test message." | 1. Navigate to the "Contact Us" section on the homepage. 2. Enter a valid name and message, leaving the email field blank. 3. Attempt to submit the form. | email blank but did not get any message |  | Failed
|  |  |  | Verify that an appropriate error message is shown when the message field is left blank. | Should display an error message indicating that the message field is required. | did not found as per expectation | Name: "John Doe" Email: "john.doe@example.com" Message: (Leave blank) | 1. Navigate to the "Contact Us" section on the homepage. 2. Enter a valid name and email, leaving the message field blank. Attempt to 3. submit the form. | ,essage blank but did not get any message |  | Failed
|  |  |  | Verify that the "Contact Us" form handles special characters in the input fields. | Should accept the special characters without any error messages and proceed with form submission. | did not found as per expectation | Name: "John #$%&'" Email: "john.doe@example.com" Message: "This is a test message with special characters: #$%&'" | 1. Navigate to the "Contact Us" section on the homepage. 2. Enter special characters in the "Name" and "Message" fields. 3. Attempt to submit the form. | did not get error handle process |  | Failed
|  |  |  | Verify in the carosol shop button perfectly work after click | should perfectly work carosoul in go to the shop page | as fer expectation | N/A | 1. go to the home page 2. click the shop button in the carosol |  |  | Passed
| Account Module |  | Sign UP As A Reader | Verify The Sign up page with valid crednetials | Should sign up successfully and go to home page | found as per expectation | Valid Credentials | 1. Go to https://book-valley-72490.web.app/signup 2. FIll the came field 3. fill up Email section 4. FIll the password 5. Upload Image and submit |  |  | Passed
|  |  |  | check the Sign-Up with Empty Name Field | User should receive an error message indicating that the Name field is required. | found as per expectation | Name: (Leave blank) Email: johndoe@example.com Password: Password123! Upload Image: Valid image file (e.g., profile.jpg) | 1. Navigate to https://book-valley-72490.web.app/signup. 2. Leave the Name field empty. 3. Enter "johndoe@example.com" in the Email field. 3. Enter "Password123!" in the Password field. 4. Upload a valid image (profile.jpg) in the Upload Image field. 5. Click on the "Sign Up" button. |  |  | Passed
|  |  |  | Check signup with an invalid email format. | User should receive an error message indicating that the Email format is invalid. | found as per expectation | Name: John Doe Email: johndoe@invalid Password: Password123! Upload Image: Valid image file (e.g., profile.jpg) | 1. Navigate to https://book-valley-72490.web.app/signup. 2. Enter "John Doe" in the Name field. 3. Enter "johndoe@invalid" in the Email field. 4. Enter "Password123!" in the Password field. 5. Upload a valid image (profile.jpg) in the Upload Image field. Click on the "Sign Up" button. |  |  | Passed
|  |  |  | Check signup with a weak password | User should receive an error message indicating that the password is too weak. | found as per expectation | Name: John Doe Email: johndoe@example.com Password: 12345 Upload Image: Valid image file ( profile.jpg) | 1. Navigate to https://book-valley-72490.web.app/signup. 2. Enter "John Doe" in the Name field. 3. Enter "johndoe@example.com" in the Email field. 4. Enter "12345" in the Password field. 5. Upload a valid image (profile.jpg) in the Upload Image field. Click on the "Sign Up" button. |  |  | Passed
|  |  |  | Check signup behavior with the Email field left empty. | User should receive an error message indicating that the Email field is required. | found as per expectation | Name: John Doe Email: (Leave blank) Password: Password123! Upload Image: Valid image file (e.g., profile.jpg) | 1. Navigate to https://book-valley-72490.web.app/signup. 2. Enter "John Doe" in the Name field. 3. Leave the Email field empty. 4. Enter "Password123!" in the Password field. 5. Upload a valid image (profile.jpg) in the Upload Image field. Click on the "Sign Up" button. |  |  | Passed
|  |  |  | Check signup with an image file that exceeds the size limit | User should receive an error message indicating that the image file is too large. | found as per expectation | Name: John Doe Email: johndoe@example.com Password: Password123! Upload Image: Large image file (e.g., large_image.jpg, 10MB) | 1. Navigate to https://book-valley-72490.web.app/signup. 2. Enter "John Doe" in the Name field. Enter "johndoe@example.com" in the Email field. 3. Enter "Password123!" in the Password field. 4. Upload a large image ( large_image.jpg, 10MB) in the Upload Image field. 5.Click on the "Sign Up" button. |  |  | Passed
|  |  |  | Check signup with special characters in the Name field. | User should be able to sign up successfully if special characters are allowed in the Name field. | found as per expectation | Name: John@Doe! Email: johndoe@example.com Password: Password123! Upload Image: Valid image file (e.g., profile.jpg) | 1. Navigate to https://book-valley-72490.web.app/signup. 2. Enter "John@Doe!" in the Name field. Enter "johndoe@example.com" in the Email field. 3. Enter "Password123!" in the Password field. 4. Upload a valid image ( profile.jpg) in the Upload Image field. 5.Click on the "Sign Up" button. |  |  | Passed
|  |  |  | Check signup with an invalid image format. | User should receive an error message indicating that the image format is invalid. | found as per expectation | Name: John Doe Email: johndoe@example.com Password: Password123! Upload Image: Invalid image file (e.g., profile.txt) | 1. Navigate to https://book-valley-2. 72490.web.app/signup. 3. Enter "John Doe" in the Name field. Enter "johndoe@example.com" in the Email field. 4.Enter "Password123!" in the Password field. 5. Upload an invalid image format ( profile.txt) in the Upload Image field. Click on the "Sign Up" button. |  |  | Passed
|  |  |  | Check signup with an email that is already registered. | User should receive an error message indicating that the email is already registered. | found as per expectation | Name: John Doe Email: existinguser@example.com Password: Password123! Upload Image: Valid image file (e.g., profile.jpg) | 1. Navigate to https://book-valley-72490.web.app/signup. 2. Enter "John Doe" in the Name field. 2. Enter "existinguser@example.com" in the Email field. 3. Enter "Password123!" in the Password field. 4. Upload a valid image ( profile.jpg) in the Upload Image field. 5. Click on the "Sign Up" button. |  |  | Passed
|  |  |  | Check signup without uploading an image. | User should be able to sign up successfully if the image upload is optional. | found as per expectation | Name: John Doe Email: johndoe@example.com Password: Password123! Upload Image: (Leave blank) | 1. Navigate to https://book-valley-72490.web.app/signup. 2. Enter "John Doe" in the Name field. Enter "johndoe@example.com" in the Email field. 3. Enter "Password123!" in the Password field. 4. Leave the Upload Image field blank. 5. Click on the "Sign Up" button. |  |  | Passed
|  |  |  | Check signup with a password shorter than the minimum required length. | User should receive an error message indicating that the password is too short. | found as per expectation | Name: John Doe Email: johndoe@example.com Password: Pass Upload Image: Valid image file (e.g., profile.jpg) | 1. Navigate to https://book-valley-72490.web.app/signup. 2. Enter "John Doe" in the Name field. 3. Enter "johndoe@example.com" in the Email field. 4. Enter "Pass" in the Password field. 5. Upload a valid image ( profile.jpg) in the Upload Image field. 6. Click on the "Sign Up" button. |  |  | Passed
|  |  |  | Check the system’s vulnerability to XSS by entering a script in the Name field. | should escape or sanitize the input and display an error if necessary. | found as per expectation | Name: <script>alert('XSS')</script> Email: johndoe@example.com Password: Password123! Upload Image: Valid image file (e.g., profile.jpg) | 1. Navigate to https://book-valley-72490.web.app/signup. 2. Enter <script>alert('XSS')</script> in the Name field. 3. Enter "johndoe@example.com" in the Email field. 4. Enter "Password123!" in the Password field. 5. Upload a valid image ( profile.jpg) in the Upload Image field. 6. Click on the "Sign Up" button. |  |  | Passed
|  |  |  | Check signup with a Name field that exceeds the character limit. | The system should either trim the Name to the maximum allowed length or display an error message if the name exceeds the limit. | Not found as per expectation | Name: Jonathan Edward Christopher Benjamin Montgomery the Third (Assuming the name exceeds the allowed limit) Email: johndoe@example.com Password: Password123! Upload Image: Valid image file (profile.jpg) | 1. Navigate to https://book-valley-72490.web.app/signup. 2. Enter a very long name in the Name field. 3. Enter "johndoe@example.com" in the Email field. 4. Enter "Password123!" in the Password field. 5. Upload a valid image ( profile.jpg) in the Upload Image field. Click on the "Sign Up" button. | Screenshot |  | Failed
|  |  |  | Check if the system correctly handles email addresses in upper case. | The system should recognize the email regardless of case sensitivity and proceed with the signup. | Not found as per expectation | Name: John Doe Email: JOHNDOE@EXAMPLE.COM Password: Password123! Upload Image: Valid image file (e.g., profile.jpg) | 1. Navigate to https://book-valley-72490.web.app/signup. 2. Enter "John Doe" in the Name field. 3. Enter "JOHNDOE@EXAMPLE.COM" in the Email field. 4. Enter "Password123!" in the Password field. 5. Upload a valid image (profile.jpg) in the Upload Image field. Click on the "Sign Up" button. |  |  | Passed
|  |  |  | Check the system's security against SQL injection by entering SQL commands in the Name field. | The system should escape or sanitize the input and display an error if necessary, preventing any SQL injection. | found as per expectation | Name: '; DROP TABLE users; -- Email: johndoe@example.com Password: Password123! Upload Image: Valid image file (e.g., profile.jpg) | 1. Navigate to https://book-valley-72490.web.app/signup. 2. Enter '; DROP TABLE users; -- in the Name field. 3. Enter "johndoe@example.com" in the Email field. 4. Enter "Password123!" in the Password field. 5. Upload a valid image (e.g., profile.jpg) in the Upload Image field. 5. Click on the "Sign Up" button. |  |  | Passed
|  |  |  | Check signup with invalid characters in the Email field | The system should display an error indicating that the Email format is invalid. | found as per expectation | Name: John Doe Email: johndoe@exam#ple.com Password: Password123! Upload Image: Valid image file (e.g., profile.jpg) | 1. Navigate to https://book-valley-72490.web.app/signup. 2. Enter "John Doe" in the Name field. 3. Enter "johndoe@exam#ple.com" in the Email field. 4. Enter "Password123!" in the Password field. 5. Upload a valid image (e.g., profile.jpg) in the Upload Image field. 6. Click on the "Sign Up" button. |  |  | Passed
|  |  | Sign In | Check the sign-in functionality with valid email and password | Email: johndoe@example.com Password: Password123! | found as per expectation | Email: johndoe@example.com Password: Password123! | 1. Navigate to the sign-in page. 2. Enter "johndoe@example.com" in the Email field. 3. Enter "Password123!" in the Password field. 4.Click on the "Sign In" button. |  |  | Passed
|  |  |  | Check sign-in with an incorrectly formatted email address. | should display an error message indicating that the email format is invalid. | found as per expectation | Email: johndoeexample.com Password: Password123! | 1. Navigate to the sign-in page. 2. Enter "Talhaexample.com" (missing @) in the Email field. 2. Enter "Password123!" in the Password field. 3. Click on the "Sign In" button. |  |  | Passed
|  |  |  | Check sign-in with an email that is not registered in the system | should display an error message indicating that the email is not registered. | found as per expectation | Email: unregistered@example.com Password: Password123! | 1. Navigate to the sign-in page. 2. Enter "unregistered@example.com" in the Email field. 3. Enter "Password123!" in the Password field. 4. Click on the "Sign In" button. |  |  | Passed
|  |  |  | Check sign-in with a valid email but an incorrect password. | should display an error message indicating that the password is incorrect. | found as per expectation | Email: johndoe@example.com Password: WrongPassword! | 1. Navigate to the sign-in page. 2. Enter "johndoe@example.com" in the Email field. 3. Enter "WrongPassword!" in the Password field. 4. Click on the "Sign In" button. |  |  | Passed
|  |  |  | Check the sign-in process when the Email field is left empty. | The system should display an error message indicating that the Email field is required. | found as per expectation | Email: (Leave this field empty) Password: Password123 | 1. Navigate to the sign-in page. Leave the Email field empty. 2. Enter "Password123!" in the Password field. 3. Click on the "Sign In" button. |  |  | Passed
|  |  |  | Check the sign-in process when the Password field is left empty. | The system should display an error message indicating that the Password field is required. | found as per expectation | Email: johndoe@example.com Password: (Leave this field empty) | 1. Navigate to the sign-in page. 2. Enter "johndoe@example.com" in the Email field. 3. Leave the Password field empty. 4. Click on the "Sign In" button. |  |  | Passed
|  |  |  | Check the system's vulnerability to SQL injection by entering SQL commands in the Email field. | The system should escape or sanitize the input and display an error if necessary, preventing any SQL injection. | found as per expectation | Email: '; DROP TABLE users; -- Password: Password123! | 1. Navigate to the sign-in page. 2. Enter '; DROP TABLE users; -- in the Email field. 3. Enter "Password123!" in the Password field. 4. Click on the "Sign In" button. |  |  | Passed
|  |  |  | Check the system’s vulnerability to XSS by entering a script in the Email field. | The system should escape or sanitize the input and display an error if necessary. | found as per expectation | Email: <script>alert('XSS')</script> Password: Password123! | 1. Navigate to the sign-in page. 2. Enter <script>alert('XSS')</script> in the Email field. 3. Enter "Password123!" in the Password field. 4. Click on the "Sign In" button. |  |  | Passed
|  |  |  | Check if the "Remember Me" option retains user credentials on the device after sign-in. | The user should remain signed in on the same device after closing and reopening the browser. | do not found as per expectation | Email: johndoe@example.com Password: Password123! | 1. Navigate to the sign-in page. 2. Enter "johndoe@example.com" in the Email field. 3. Enter "Password123!" in the Password field. 4. Check the "Remember Me" option. 5. Click on the "Sign In" button. 6. Close and reopen the browser. 7. Verify that the user remains signed in. | screenshot |  | Failed
|  |  |  | Check if the password field is case-sensitive. | The system should reject the sign-in attempt if the password case does not match exactly with the registered password | found as per expectation | Email: johndoe@example.com Password: PASSWORD123! (Different case from the registered "Password123!") | 1. Navigate to the sign-in page. 2. Enter "johndoe@example.com" in the Email field. 3. Enter "PASSWORD123!" (uppercase) in the Password field. 4. Click on the "Sign In" button. |  |  | Passed
|  |  |  | Verify that the sign-up page loads correctly and displays all required fields. | The system should allow sign-in with a copied and pasted password, as long as the password is correct. | found as per expectation | Email: johndoe@example.com Password: (Paste "Password123!" from clipboard) | 1. Copy "Password123!" to the clipboard. 2. Navigate to the sign-in page. 3. Enter "johndoe@example.com" in 4. the Email field. Paste "Password123!" into the Password field. 5. Click on the "Sign In" button. |  |  | Passed
|  |  |  | Check if the system correctly handles sign-in when credentials are auto-filled by the browser. | The system should successfully sign in the user with the auto-filled credentials | found as per expectation | Email: johndoe@example.com (auto-filled by browser) Password: Password123! (auto-filled by browser) | 1. Ensure that your browser has saved credentials for the email 2. "johndoe@example.com". Navigate to the sign-in page. 3. Allow the browser to auto-fill the Email and Password fields. 4. Click on the "Sign In" button. |  |  | Passed
|  |  |  | Check the sign-in functionality on a mobile browser. | The sign-in form should be fully functional and properly formatted on a mobile browser, allowing the user to sign in successfully. | found as per expectation | Email: johndoe@example.com Password: Password123! | 1. Open the sign-in page on a mobile browser. 2. Enter "johndoe@example.com" in the Email field. 3. Enter "Password123!" in the Password field. 4. Click on the "Sign In" button. |  |  | Passed
|  |  |  | Check the sign-in functionality under slow internet conditions. | should handle the sign-in process smoothly, possibly with a loading indicator, and eventually sign in the user successfully. | found as per expectation | Email: john doe @example. com Password: Passw ord123! | 1. Simulate a slow internet connection. 2. Navigate to the sign-in page. 3. Enter "johndoe@example. com" in the Email field. 3. Enter "Password123!" in the Password field. 4. Click on the "Sign In" button. |  |  | Passed
|  |  |  | check sign in with google functionality perfectly works | should sign up with google successfully | found as per expectation | N/A | 1. go to url: https://book-valley-72490.web.app/login 2. click the continue with the google |  |  | Passed
|  |  | SIgn up as writer |  | All fields (Name, Email, Password, Phone, Profile Photo, Bank Account, Bank Details) are displayed on the sign-up page. | found as per expectaion | N/A | 1. Open the web browser. 2. Navigate to the sign-up page URL. 3. Verify that all required fields are present. |  |  | Passed
|  |  |  | Verify that the Name field accepts valid input. | The Name field accepts valid input without errors | found as per expectaion | Name: Md. Abu Talha | 1. Navigate to the sign-up page. 2. Enter "Md. Abu Talha" in the 3. Name field. 4. Verify that the input is accepted 5. without any error messages. |  |  | Passed
|  |  |  | Verify that the Email field accepts a valid email address. | The Email field accepts a valid email format (user@example.com). | found as per expectaion | Email: abutalha@example.com | 1. Navigate to the sign-up page. 2. Enter "abutalha@example.com" in the Email field. 3. Verify that the input is accepted without any error messages. |  |  | Passed
|  |  |  | Verify that the Email field displays an error message when an invalid email is entered. | The system displays an appropriate error message for invalid email formats. | found as per expectaion | Email: abutalha@invalid | 1. Navigate to the sign-up page. 2. Enter "abutalha@invalid" in the Email field. 3. Try to submit the form. 4. Verify that an error message is 5. displayed for the invalid email format. |  |  | Passed
|  |  |  | Verify that the Password field accepts input and masks it with dots or asterisks. | The Password field displays the input as masked characters. | found as per expectaion | Password: P@ssw0rd123 | 1. Navigate to the sign-up page. 2. Enter "P@ssw0rd123" in the Password field. 3. Verify that the input is displayed as masked characters. |  |  | Passed
|  |  |  | Verify that the Password field enforces minimum password strength criteria. | The system displays an error if the password does not meet the minimum strength requirements (e.g., length, special characters). | found as per expectaion | Password: short1 | 1. Navigate to the sign-up page. 2. Enter "short1" in the Password field. 3. Try to submit the form. 4. Verify that an error message is displayed indicating that the password is too weak. |  |  | Passed
|  |  |  | Verify that the Phone field accepts a valid phone number format | The Phone field accepts a valid phone number ( numeric, specific length). | found as per expectaion | Phone: 01310105350 | 1. Navigate to the sign-up page. 2. Enter "01310105350" in the Phone field. 3. Verify that the input is accepted without any error messages. |  |  | Passed
|  |  |  | Verify that the Phone field displays an error message when an invalid phone number is entered. | The system displays an error for an invalid phone number format. | did not found as per expectation | Phone: 12345abc | 1. Navigate to the sign-up page. 2. Enter "12345abc" in the Phone field. 3. Try to submit the form. 4. Verify that an error message is displayed for the invalid phone number format. | https://drive.google.com/file/d/1vmRT4dZSuuIqFY8BQ3ffj0Ah0oTkfXVE/view?usp=sharing |  | Failed
|  |  |  | Verify that the Profile Photo field allows users to upload a valid image file. | The system allows uploading and displays the selected image or filename. |  | profile_pic.jpg (JPEG, PNG format) | 1. Navigate to the sign-up page. 2. Click on the Profile Photo upload button. 3. Select a valid image file (e.g., profile_pic.jpg). 4. Verify that the file is accepted and displayed. |  |  | Not Executed
|  |  |  | Verify that the system displays an error when an invalid file type is uploaded in the Profile Photo field. | The system displays an error when a non-image file (exe, .docx) is uploaded. |  | invalid_file.exe | Navigate to the sign-up page. 2. Click on the Profile Photo upload button. 3. Select an invalid file type (e.g., invalid_file.exe). 4. Verify that an error message is displayed, rejecting the file upload. |  |  | Not Executed
|  |  |  | Verify that the Bank Account field accepts a valid numeric account number | The Bank Account field accepts a valid numeric input without errors. |  | Bank Account: 01234567890123456 | 1. Navigate to the sign-up page. 2. Enter "01234567890123456" in the Bank Account field. 3. Verify that the input is accepted without any error messages. |  |  | Not Executed
|  |  |  | Verify that the Bank Account field displays an error when non-numeric data is entered. | The system displays an error message when non-numeric data is entered in the Bank Account field. |  | Bank Account: ABC12345XYZ | 1. Navigate to the sign-up page. 2. Enter "ABC12345XYZ" in the Bank Account field. 3. Try to submit the form. 4. Verify that an error message is displayed for invalid account number format. |  |  | Not Executed
|  |  |  | Verify that the Bank Details field accepts valid input (text, numbers) | The Bank Details field accepts valid input without errors. |  | ABC Bank, Branch: XYZ, Swift Code: ABCDXYZ | 1. Navigate to the sign-up page. 2. Enter "ABC Bank, Branch: XYZ, Swift Code: ABCDXYZ" in the Bank Details field. 3. Verify that the input is accepted without any error messages. |  |  | Not Executed
|  |  |  | Verify that the form submits successfully when all fields are filled with valid data | The form submits successfully, and a confirmation message is displayed, or the user is redirected appropriately |  | Name: Md. Abu Talha - Email: abutalha@example.com - Password: P@ssw0rd123 - Phone: 01310105350 - Profile Photo: profile_pic.jpg - Bank Account: 01234567890123456 - Bank Details: ABC Bank, Branch: XYZ, Swift Code: ABCDXYZ | 1. Navigate to the sign-up page. 2. Fill in all the fields with valid data. 3. Click the "Submit" button. 4. Verify that the form is submitted successfully and that a confirmation message is displayed, or the user is redirected. |  |  | Not Executed
|  |  |  | Verify that the form displays error messages when required fields are left blank and the form is submitted | Should throgh the appropriate error |  | N/A | Verify that the form displays error messages when required fields are left blank and the form is submitted |  |  | Not Executed
|  |  |  | Verify that the Name field is not vulnerable to XSS attacks | The system sanitizes the input, and no script is executed. An error message is displayed or the script is shown as plain text. |  | Name: <script>alert('XSS');</script> | Navigate to the sign-up page. Enter <script>alert('XSS');</script> in the Name field. Try to submit the form. Verify that the script is not executed and that it is either sanitized or displayed as plain text |  |  | Not Executed
|  |  |  | Verify that the Email field is not vulnerable to XSS attacks. | The system sanitizes the input, and no script is executed. An error message is displayed or the script is shown as plain text. |  | Email: <script>alert('XSS');</script> | 1. Navigate to the sign-up page. 2. Enter <script>alert('XSS');</script> in the Email field. 3. Try to submit the form. 4. Verify that the script is not 5. executed and that it is either sanitized or displayed as plain text. |  |  | Not Executed
|  |  |  | Verify that the Email field is not vulnerable to SQL injection attacks | The system sanitizes the input, and no SQL commands are executed. An error message is displayed for invalid input. |  | test@example.com' OR '1'='1 | 1. Navigate to the sign-up page. 2. Enter test@example.com' OR '1'='1 in the Email field. 3. Try to submit the form. 4. Verify that no SQL commands are executed and that the system either 5. rejects the input or displays an error message. |  |  | Not Executed
|  |  |  | Verify that the Bank Account field is not vulnerable to SQL injection attacks. | The system sanitizes the input, and no SQL commands are executed. An error message is displayed for invalid input. |  | Bank Account: 123456'; DROP TABLE users; -- | 1. Navigate to the sign-up page. 2. Enter 123456'; DROP TABLE users; -- in the Bank Account field. Try to submit the form. 3. Verify that no SQL commands are 4.executed and that the system either rejects the input or displays an error message. |  |  | Not Executed
| Shop |  | Category & SearchBar | Verify that the Shop Category dropdown is visible and contains all the required categories. | The dropdown is visible, and all categories are listed correctly |  | N/A | Navigate to the Shop page. Check if the Category dropdown is visible. Click on the dropdown. Verify that the following categories are listed: Adventure Fiction Romance Fantasy Religion Thriller History Educational |  |  | Not Executed
|  |  |  | Verify Category Selection Functionality | Products displayed correspond to the selected category. |  | Select different categories (Adventure, Fiction). | Open the Shop page. Click the Category dropdown. Select the category "Adventure". Verify that products under the "Adventure" category are displayed. Repeat for other categories. |  |  | Not Executed
|  |  |  | Verify Default Category Selection | All Categories or no category is pre-selected. |  | N/A | Open the Shop page. Check if the default selection is either "All Categories" or no category selected. |  |  | Not Executed
|  |  |  | Varify Category Count in Dropdown | should be 8 categories listed in the dropdown. |  | N/A | Navigate to the Shop page. Click on the Category dropdown. Count the categories listed. |  |  | Not Executed
|  |  |  | Verify Searchbar Visibility and Functionality | Ensure the searchbar is visible and allows text input. |  | N/A | 1. Navigate to the Shop page. 2. Check if the searchbar is visible. 3. Click inside the searchbar and input any keyword (e.g., "Adventure"). 4. Press "Enter" or click the search icon. |  |  | Not Executed
|  |  |  | verify Search with Valid Input | Products related to the entered keyword are displayed. |  | N/A | 1. Navigate to the Shop page. 2. Type "Adventure" in the searchbar and hit "Enter". 3. Observe the search results. 4. Repeat with other valid keywords like "Fiction" and "Thriller". |  |  | Not Executed
|  |  |  | Validate Search with Invalid Input | No products are displayed, and a "No results found" message is shown. |  | Input "abcxyz". | Navigate to the Shop page. Type "abcxyz" in the searchbar and hit "Enter". |  |  | Not Executed
|  |  |  | Validate Search with Special Characters | The system either handles special characters gracefully or shows a "No results found" message without errors. |  | Input special characters like "@#$%^&* | The system either handles special characters gracefully or shows a "No results found" message without errors. |  |  | Not Executed
|  |  |  | Validate Search with Empty Input | No search is performed, and the current page remains unchanged. |  | Leave the searchbar empty. | 1. Navigate to the Shop page. 2. Click the search icon or press 3. "Enter" without entering any text. |  |  | Not Executed
|  |  |  | Verify Dropdown Sorting Order | Categories are listed in alphabetical order or as per the expected business rule. |  | N/A | Navigate to the Shop page. Open the Shop Category dropdown. Review the order of categories. |  |  | Not Executed
|  |  |  | Validate Dropdown Selection Persistence | The selected category persists after navigation and page reload. |  | N/A | 1. Open the Shop page. 2. Select "Fiction" from the 3. Category dropdown. 4. Navigate to another page (,5. Product details page). Navigate back to the Shop page and check if "Fiction" remains selected. Reload the page and verify if the selection persists. |  |  | Not Executed
|  |  |  | Validate Dropdown Functionality on Mobile Devices | The dropdown is responsive and functional on mobile devices, and category selection works as expected. |  | N/A | 1. Access the Shop page on a mobile device or emulator. 2. Tap on the Category dropdown. Select a category. 3. Observe the behavior. |  |  | Not Executed
|  |  |  | Verify Accessibility of Dropdown for Keyboard Navigation | The dropdown is accessible using keyboard navigation and functions properly. |  | N/A | 1. Navigate to the Shop page. 2. Use the "Tab" key to focus on the 3. Category dropdown. 4. Use the Arrow keys to navigate through the categories. 5. Select a category using the "Enter" key. |  |  | Not Executed
|  |  |  | Validate Search Suggestions Autocomplete | Relevant search suggestions appear as the user types based on the entered characters. |  | Start typing "Adv", "Fic". | Navigate to the Shop page. Start typing "Adv" or "Fic" in the searchbar. Observe the suggested search terms or products. |  |  | Not Executed
|  |  |  | Validate Searchbar Case Sensitivity | The same search results should appear for all three inputs regardless of case. |  | "Adventure", "adventure", "ADVENTURE". | 1. Navigate to the Shop page. 2. Search using "Adventure". 3. Search using "adventure". 4. Search using "ADVENTURE". |  |  | Not Executed
|  |  |  | Verify Search Functionality with Multiple Keywords | Products related to both "Fiction" and "Adventure" categories are displayed. |  | Search for "Fiction Adventure". | Navigate to the Shop page. Enter "Fiction Adventure" in the searchbar and hit "Enter". |  |  | Not Executed
|  |  |  | Validate Search Result Sorting and Filtering | The search results are sorted and filtered correctly based on the user's selection. |  | N/A | 1.Search for a term in the searchbar (e "Fiction"). 2. Apply sorting ("Price: Low to High"). 3. Apply filtering ( "4-star rating and above"). |  |  | Not Executed
Not Executed
| Cart |  | Cart | Verify Book Image Display | The book image is visible for all items in the cart. |  | Various books added to the cart. | 1. Add books to the cart. 2. Navigate to the Cart page. 3. Verify the image is displayed next to each book. |  |  | Not Executed
|  |  |  | Verify that the name of each book in the cart is displayed correctly | The correct book name is displayed for all items in the cart. |  | Different book names in the cart. | 1. Add books to the cart. 2. Navigate to the Cart page. 3. Check that the correct book name is displayed. |  |  | Not Executed
|  |  |  | Verify Category Display | The category is displayed for all books in the cart. |  | Books from different categories added to the cart. | 1. Add books from different categories to the cart. 2. Navigate to the Cart page. 3. Check the displayed category of each book. |  |  | Not Executed
|  |  |  | Verify Writer Display | The correct writer's name is displayed for all books. |  | Various books with different writers added to the cart. | 1. Add books to the cart. 2.Navigate to the Cart page. 3. Verify the writer's name is displayed correctly. |  |  | Not Executed
|  |  |  | Various books with different writers added to the cart. | Users can successfully increase or decrease the quantity of books in the cart. Test Data: Add a book to the cart. |  | Add book to the cart | Add books to the cart. Modify the quantity and check if it updates. Verify that the total price updates based on the quantity. |  |  | Not Executed
|  |  |  | Verify Price Update with Quantity Change | The price updates dynamically as the quantity changes. |  | Add a book with a known price to the cart. | Increase or decrease the quantity of the book. Verify that the total price updates accordingly. |  |  | Not Executed
|  |  |  | Verify Coupon Code Input Field | The coupon code input field is visible, and users can enter a code |  | N/A | 1.Navigate to the Cart page. 2. Check for the presence of the coupon code input field |  |  | Not Executed
|  |  |  | Apply Valid Coupon Code | The valid coupon code is applied, and the discount is reflected in the total. |  | Valid coupon code "DISCOUNT10". | 1. Enter a valid coupon code in the cart. 2. Click "Apply Coupon". 3. Verify that the discount is applied and the total is updated. |  |  | Not Executed
|  |  |  | Apply Invalid Coupon Code | The system shows an appropriate error message when an invalid coupon code is used. |  | Invalid couppn | 1. Enter an invalid coupon code in the cart. 2. Click "Apply Coupon". 3. Verify that an error message is displayed. |  |  | Not Executed
|  |  |  | Verify Subtotal Calculation | The subtotal reflects the correct total price before any discounts or taxes. |  | Multiple books in the cart with known prices. | 1. Add books to the cart. 2. Verify that the subtotal is calculated 3based on the quantity and price. |  |  | Not Executed
|  |  |  | Verify Tax Calculation in Order Details | The tax is displayed correctly in the order details. |  | Known tax rate | 1. Add books to the cart. 2. Verify that the tax is calculated and displayed correctly. |  |  | Not Executed
|  |  |  | Verify Total Calculation in Order Details | The total is displayed correctly, reflecting the final amount after all discounts and taxes |  | Known prices and tax rates. | 1. Add books to the cart. 2. total is correctly calculated. |  |  | Not Executed
|  |  |  | Verify Checkout Button Functionality | Clicking the "Checkout" button redirects users to the payment page. |  | Multiple books in the cart. | 1. Add books to the cart. 2. Click on the "Checkout" button. 3. Verify that the user is redirected to the payment page. |  |  | Not Executed
|  |  |  | Verify Empty Cart Message | The user sees an appropriate "Cart is empty" message when there are no items in the cart. |  | Empty cart. |  |  |  | Not Executed
Negative test
mmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmm

## Bug Report
Bug Reporting
# SL 01
Issue: Registered with invalid email address.
Reproducing Steps:
1. Goto the URL https:/www.startech.com.bd 2. Click on the Register button at the right corner. 3. Fill all the files with valid credentials. 4. Click 'Continue'.
Env: Production.
Module: Register
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshot: Invalid email address error
Expected: Should not allow registration with invalid email address.
Responsible QA: Tashfiquzzman
Bug Reporting
# SL 02
Issue: Click on "Forgotten Password?" and Account deleted
Reproducing Steps:
1. Goto the URL https://www.startech.com.bd 2. Click on the Login button at the right corner 3. Fill all the fields with invalid credentials 4. Click ''Forgotten Password?"
Env: Production
Module: Login
Severity: P2
Screenshot: "Forgotten Password" error
Responsible QA: Tashfiquzzaman
Responsible QA: Tashfiquzzaman
Responsible QA: Tashfiquzzaman
Responsible QA: Tashfiquzzaman
Bug Reporting
# SL 03
Issue: First and last names should not start with a special character.
Reproducing Steps:
1. Goto the URL https:/www.startech.com.bd 2. Click on the Register button at the right corner. 3. Fill all the fiels with valid credentials
4. Click 'Continue'.
Env: Production.
Module: Register
Severity: P4
Screenshot: First and last names should not start with a special characte
Responsible QA: Tashfiquzzman
Bug Reporting
# SL 04
issue:First name and last name should not start with number.
Reproducing Steps:
1. Goto the URL https://www.startech.com.bd 2. Click on the Login button at the right corner 3. Fill all the fields with invalid credentials 4. Click ''Forgotten Password?"
Env: Production
Module: Login
Severity: P5
Screenshot: First name error
Responsible QA: Tashfiquzzaman
Bug Reporting
# SL 05
issue: A comma should not be expected between the name field.
Reproducing Steps:
1. Goto the URL https://www.startech.com.bd 2. Click on the Login button at the right corner 3. Fill all the fields with invalid credentials 4. Click ''Forgotten Password?"
Env: Production
Module: Login
Severity: P6
Screenshot: Comma error in first name.
Responsible QA: Tashfiquzzaman
Bug Reporting
# SL 01
Issue: Registered with invalid email address.
Reproducing Steps:
1. Goto the URL https:/www.startech.com.bd 2. Click on the Register button at the right corner. 3. Fill all the files with valid credentials. 4. Click 'Continue'.
Env: Production.
Module: Register
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshot: Invalid email address error
Expected: Should not allow registration with invalid email address.
Responsible QA: Tashfiquzzman